# TactiTok MVP — Sprint Plan

8–12 Weeks · 6 Sprints · 3 Developers · 12 Acceptance Criteria

## Developer Legend

| FE | Frontend (Vanilla JS + HTML) |
| --- | --- |
| NGINX | Edge Server (nginx) |
| API | Backend (FastAPI + PostgreSQL) |
| ALL | All Three Devs |

## Sprint Overview

| Sprint | Weeks | Goal | Milestone |
| --- | --- | --- | --- |
| Sprint 1 | 1–2 | Foundation | M1: Everything Starts |
| Sprint 2 | 3–4 | Content Pipeline | M2: Content Pipeline Works |
| Sprint 3 | 5–6 | Reels Experience ⚠ | M3: Reels on Device ⚠ HIGHEST RISK |
| Sprint 4 | 7–8 | Downloads & Offline | M4: Full Offline Loop |
| Sprint 5 | 9–10 | Admin Polish + Integration | M5: Demo Script Passes |
| Sprint 6 | 11–12 | Stabilisation & Demo Prep | M6: Demo Ready |

Sprint Details

## Sprint 1 — Foundation

Goal: All three components running and talking to each other. Cloud API reachable, edge nginx proxying, tablet and admin PC can open HTML pages in Chrome.

| Week | Task | Dev |
| --- | --- | --- |
| W1 | Set up FastAPI project, virtual environment, and folder structure | API |
| W1 | Create PostgreSQL schema: content, categories, interests tables | API |
| W1 | Implement GET /health endpoint | API |
| W1 | Implement skeleton upload endpoint (accept file, save to disk, return 200) | API |
| W1 | Install nginx on edge VM; configure to serve placeholder HTML to Chrome on tablet | NGINX |
| W1 | Configure nginx as reverse proxy pointing at the cloud API | NGINX |
| W1 | Confirm tablet opens Chrome at edge VM address and sees placeholder page | NGINX |
| W1 | Build static admin upload form (file picker, title, submit button) | FE |
| W1 | Configure FastAPI to serve admin HTML as a static file | API |
| W2 | nginx successfully proxies GET /health through to cloud API — confirm end-to-end | NGINX |
| W2 | Admin opens Chrome on Windows PC and sees upload form | FE |
| W2 | Form posts to skeleton upload endpoint and shows success/error message | FE |
| W2 | Resolve any port-forwarding or firewall issues between tablet → edge VM → cloud | NGINX |
| W2 | Deploy cloud VM, confirm public reachability (PR4 mitigation) | API |
| W2 | Write M1 exit checklist and verify all 5 criteria pass | ALL |

Exit Criteria

- GET /health on cloud API returns 200

- Skeleton upload endpoint accepts a file and saves it to disk

- nginx proxies GET /health from the cloud successfully

- Tablet opens Chrome and sees an HTML page served from edge VM

- Admin opens Chrome on Windows PC and sees the upload form

Milestone 1: M1: Everything Starts

## Sprint 2 — Content Pipeline

Goal: A file uploaded through the admin form must appear in the catalog and be playable/viewable on the edge device. Range request support for video confirmed.

| Week | Task | Dev |
| --- | --- | --- |
| W3 | Implement GET /catalog (returns title, type, category, interests, version, file URL) | API |
| W3 | Implement GET /content/{id}/file with HTTP 206 range request support | API |
| W3 | Implement full POST /content (file + metadata) | API |
| W3 | Implement PUT /content/{id} and DELETE /content/{id} | API |
| W3 | Implement CRUD endpoints for categories and interests | API |
| W3 | Add thumbnail generation or URL field for video files | API |
| W3 | JS: fetch GET /catalog on page load and store in memory array | FE |
| W3 | Render flat list of content cards in library view | FE |
| W4 | Clicking a video card opens HTML5 <video> player | FE |
| W4 | Clicking a PDF card opens file in-browser via PDF.js | FE |
| W4 | Add manual refresh button to re-fetch catalog | FE |
| W4 | Admin portal: full upload form (file, title, description, category, interests, progress bar) | FE |
| W4 | Admin portal: content list page — table of uploaded items with delete button | FE |
| W4 | Admin portal: edit form — pre-filled metadata, PUT request on submit | FE |
| W4 | Admin portal: category and interest management pages | FE |
| W4 | Configure nginx to cache content files; confirm second request is served from cache | NGINX |
| W4 | Verify HTTP 206 range response in browser DevTools (required for video + nginx cache) | NGINX |

Exit Criteria

- Upload a video via admin form → appears in GET /catalog

- Upload a PDF via admin form → appears in GET /catalog

- Edge client fetches catalog → items appear in library list on tablet

- Video streams with range requests (HTTP 206 confirmed in DevTools)

- PDF opens and renders in-browser on tablet

- Delete an item in admin → removed from catalog on next sync

- nginx caches a content file — second request served from cache

Milestone 2: M2: Content Pipeline Works

## Sprint 3 — Reels Experience ⚠

Goal: TikTok-style feed validated hands-on on the 10" tablet. CSS scroll-snap, IntersectionObserver, auto-play policy, and touch gestures must all work together on real hardware.

⚠ HIGHEST-RISK SPRINT. Build and test the scroll-snap prototype on real hardware in week 5 before building the rest. If M3 is at risk by end of week 6 → pull de-scope levers immediately.

| Week | Task | Dev |
| --- | --- | --- |
| W5 | Prototype: full-screen vertical layout with CSS scroll-snap-type: y mandatory | FE |
| W5 | Prototype: each video as <video> element sized to 100vh | FE |
| W5 | Prototype: IntersectionObserver (threshold 0.7) — pause all, play entering video | FE |
| W5 | ⚠ Test scroll-snap prototype hands-on on real 10" tablet — confirm no jank | FE |
| W5 | Tap-to-start overlay on first load (Chrome auto-play policy) — PR2 mitigation | FE |
| W5 | Overlay UI per video: title, Like button, Save button, Download button | FE |
| W5 | Confirm nginx correctly caches range requests for video (PR3 mitigation) | NGINX |
| W6 | Video prefetch: when a video reaches 30% playback, preload next video src | FE |
| W6 | Interest selection screen: checkboxes stored in localStorage, filters feed | FE |
| W6 | Feed empty state message when no videos match selected interests | FE |
| W6 | Library: two-level collapsible category tree from catalog data | FE |
| W6 | Library: content type badges (VIDEO / PDF) on each card | FE |
| W6 | Library: text search bar filtering in-memory catalog array as user types | FE |
| W6 | Library: download button on each card; empty state message | FE |
| W6 | Full hands-on M3 validation on tablet — reels, swipe, interest filter | ALL |

Exit Criteria

- Reels feed scrolls smoothly on 10" tablet — no jank; confirmed hands-on

- First video starts within ≤ 2s on a reasonable network connection

- Auto-play works after first user tap (Chrome policy satisfied)

- Swipe up → next video snaps; swipe down → previous video

- Interest selection: choose 2 interests → feed shows only matching videos

- Library category tree: tap a category → list filters to that category

- Text search: type a term → list filters within 1s (client-side)

- Video prefetch: swiping to next video starts noticeably faster

Milestone 3: M3: Reels on Device ⚠ HIGHEST RISK

## Sprint 4 — Downloads & Offline

Goal: Close the offline loop. Download a file → nginx caches it fully → play/view it with zero network. Offline test: stop cloud server, confirm tablet still plays downloaded content.

| Week | Task | Dev |
| --- | --- | --- |
| W7 | Download button: full fetch of file URL to force nginx to cache the entire file | FE |
| W7 | On completion: store DownloadRecord in IndexedDB {id, title, type, version, cachedUrl} | FE |
| W7 | Download progress bar via XHR or fetch with ReadableStream | FE |
| W7 | Downloads tab: list all DownloadRecords — title, type, file size, date downloaded | FE |
| W7 | Play/view downloaded item from nginx-cached URL | FE |
| W7 | Delete downloaded item: remove DownloadRecord from IndexedDB | FE |
| W7 | Configure nginx stale-cache directives (proxy_cache_use_stale) | NGINX |
| W7 | Test: stop cloud server → confirm HTML/JS/CSS still loads from nginx (served from disk) | NGINX |
| W7 | Test: stop cloud server → confirm catalog served stale from nginx cache | NGINX |
| W8 | Network status indicator: poll GET /health every 30s; show online/offline banner | FE |
| W8 | Offline messaging in Reels and Library when cloud is unreachable | FE |
| W8 | "Updated" badge: compare DownloadRecord.version with catalog version | FE |
| W8 | Orphan cleanup: if a downloaded item is deleted from catalog, remove from IndexedDB on sync | FE |
| W8 | PDF page navigation: previous/next buttons, page counter (PDF.js page API) | FE |
| W8 | Document nginx stale-cache config in notes/decisions.md | NGINX |
| W8 | Load test: 5 concurrent video streams; switch to nginx X-Accel-Redirect if needed | NGINX |
| W8 | M4 offline validation: download video + PDF, disconnect network, play/view both | ALL |

Exit Criteria

- Download a video → progress bar completes → appears in Downloads tab

- Download a PDF → appears in Downloads tab

- Disconnect network → Downloads tab is fully usable

- Tap a downloaded video → plays without any network connection

- Tap a downloaded PDF → renders without any network connection

- Offline banner appears in Reels and Library views when disconnected

- "Updated" badge appears when admin updates a file the user has downloaded

- Delete a downloaded item → removed from Downloads tab and IndexedDB

Milestone 4: M4: Full Offline Loop

## Sprint 5 — Admin Polish + Integration

Goal: Full end-to-end run of the 15-step demo script without errors in a staging environment. Any AC still failing must be escalated — no time to leave problems for Sprint 6.

| Week | Task | Dev |
| --- | --- | --- |
| W9 | Test all API endpoints end-to-end; fix validation gaps (MIME type, file size, depth) | API |
| W9 | Video duration validation — reject files longer than 180s | API |
| W9 | Consistent error responses across all endpoints | API |
| W9 | Configure cloud VM HTTPS with a valid TLS certificate | API |
| W9 | Admin portal: category reorder; enforce 2-level maximum in UI | FE |
| W9 | Admin portal: interest management — add, edit, delete | FE |
| W9 | Admin portal: content list — filter by type, sort by date | FE |
| W9 | Admin portal: clear validation messages, progress bar, confirm success/failure | FE |
| W9 | Admin portal: content update workflow — replace file and increment version | FE |
| W10 | Run full 15-step demo script on actual tablet in staging — fix any UX issues | ALL |
| W10 | Measure video playback start time with a stopwatch (AC-3: ≤ 2s) | ALL |
| W10 | Run demo a second time with simulated poor connectivity | ALL |
| W10 | Document which ACs pass and which are escalated to stakeholder | ALL |
| W10 | Confirm edge VM nginx serving files and proxying to cloud correctly | NGINX |
| W10 | Fix any remaining integration issues found during demo walkthroughs | ALL |

Exit Criteria

- All API endpoints respond correctly (tested manually)

- Full 15-step demo script runs end-to-end without errors on staging

- All 12 acceptance criteria are documented as passing or escalated

- Cloud VM reachable via HTTPS

- Edge VM nginx running, serving files, and proxying correctly

Milestone 5: M5: Demo Script Passes

## Sprint 6 — Stabilisation & Demo Prep

Goal: Make the demo airtight. Load 15 real demo items, rehearse twice, fix anything that breaks. Two buffer days reserved at end of week 12 for last-minute fixes.

| Week | Task | Dev |
| --- | --- | --- |
| W11 | Load all 15 demo items: 10 PDFs + 5 videos; assign category and interests | ALL |
| W11 | Verify every item in catalog, library view, and reels feed | ALL |
| W11 | Verify thumbnails display correctly for all items | FE |
| W11 | Performance tuning: measure and optimise video start time, scroll smoothness, swipe | FE |
| W11 | Configure Chrome kiosk mode: no address bar, no OS interactions | NGINX |
| W11 | Confirm edge VM services restart automatically after device reboot | NGINX |
| W11 | Pre-warm nginx cache: download all 15 items to guarantee offline availability | NGINX |
| W11 | Re-run all API endpoint tests after demo content is loaded | API |
| W11 | Confirm cloud VM stability: FastAPI via systemd, TLS configured, DB backed up | API |
| W11 | Fix any regressions found | ALL |
| W12 | Demo rehearsal #1 on actual demo device — complete 15-step script | ALL |
| W12 | Fix all blocking issues found in rehearsal #1 | ALL |
| W12 | Demo rehearsal #2 on actual demo device — confirm all 12 AC pass | ALL |
| W12 | 2-day buffer: last-minute fixes only — no new features | ALL |
| W12 | Final sign-off: 15 items loaded · rehearsed twice · all 12 AC green · device stable | ALL |

Exit Criteria

- 15 demo items loaded and navigable across all three views (AC-10)

- All 12 acceptance criteria pass on the actual demo device

- Demo rehearsal completed twice with no blocking issues

- Chrome kiosk mode confirmed: no external apps, pop-ups, or OS interactions (AC-11)

- Edge VM restarts and all services come back up automatically

Milestone 6: M6: Demo Ready